# Implementation Checklist

Donation Management System Improvement Project

This checklist covers all tasks required to implement the Donation Management System across 5 key improvement areas. Use this to track progress and ensure nothing is missed.

# Phase 1: Planning (Weeks 1-2)

| Task | Owner | Timeline | Status |
| --- | --- | --- | --- |
| Form implementation team | Project Lead | Week 1 | ☐ |
| Review current state assessment | Project Lead | Week 1 | ☐ |
| Define success metrics and targets | Project Lead | Week 1 | ☐ |
| Secure budget for materials/supplies | Project Lead | Week 1 | ☐ |
| Schedule volunteer training sessions | Coordinator | Week 1-2 | ☐ |
| Create communication plan | Coordinator | Week 2 | ☐ |
| Set up Google Workspace account | IT Volunteer | Week 2 | ☐ |
| Prepare training materials | Project Lead | Week 2 | ☐ |

# Phase 2: Setup (Weeks 3-6)

## Area 1: Inventory Tracking System

| Task | Owner | Timeline | Status |
| --- | --- | --- | --- |
| Set up laptop at intake area | IT Volunteer | Week 3 | ☐ |
| Install Microsoft Excel | IT Volunteer | Week 3 | ☐ |
| Create DonationTracker workbook | IT Volunteer | Week 3 | ☐ |
| Configure data validation lists | IT Volunteer | Week 3 | ☐ |
| Set up conditional formatting | IT Volunteer | Week 3 | ☐ |
| Create category lookup tables | IT Volunteer | Week 3 | ☐ |
| Test intake logging process | Project Lead | Week 4 | ☐ |
| Train volunteers on tracker use | Project Lead | Week 4-5 | ☐ |
| Create intake procedure guide | Project Lead | Week 4 | ☐ |
| Print donor receipt template | Coordinator | Week 4 | ☐ |
| Set up daily handover checklist | Coordinator | Week 5 | ☐ |
| Go live with tracking system | Project Lead | Week 6 | ☐ |

## Area 2: Storage Optimization

| Task | Owner | Timeline | Status |
| --- | --- | --- | --- |
| Measure storage area dimensions | Project Lead | Week 3 | ☐ |
| Create zone layout plan | Project Lead | Week 3 | ☐ |
| Purchase shelving units (8 units) | Coordinator | Week 3 | ☐ |
| Purchase storage bins (50 bins) | Coordinator | Week 3 | ☐ |
| Purchase floor marking tape | Coordinator | Week 3 | ☐ |
| Purchase labeling supplies | Coordinator | Week 3 | ☐ |
| Schedule stock-out day | Project Lead | Week 4 | ☐ |
| Remove all items from storage | All Volunteers | Week 4 | ☐ |
| Install shelving units | IT Volunteer | Week 4 | ☐ |
| Mark zone boundaries with tape | Volunteers | Week 4 | ☐ |
| Sort and categorize all items | All Volunteers | Week 4 | ☐ |
| Place items in designated zones | All Volunteers | Week 4 | ☐ |
| Label all zones and containers | Volunteers | Week 5 | ☐ |
| Create storage map/photography | Coordinator | Week 5 | ☐ |
| Post laminated quick-reference guide | Coordinator | Week 5 | ☐ |
| Conduct safety inspection | Project Lead | Week 5 | ☐ |

## Area 3: Volunteer & Donor Coordination

| Task | Owner | Timeline | Status |
| --- | --- | --- | --- |
| Set up Google Calendar | IT Volunteer | Week 3 | ☐ |
| Create calendar categories | Coordinator | Week 3 | ☐ |
| Set up Google Forms for availability | IT Volunteer | Week 3 | ☐ |
| Create volunteer contact database | Coordinator | Week 3 | ☐ |
| Design shift structure (3-hour blocks) | Project Lead | Week 3 | ☐ |
| Create WhatsApp group for volunteers | Coordinator | Week 4 | ☐ |
| Set up dedicated phone number | Project Lead | Week 4 | ☐ |
| Create email distribution lists | Coordinator | Week 4 | ☐ |
| Design donor drop-off time slots | Project Lead | Week 4 | ☐ |
| Create donor information sheet | Coordinator | Week 4 | ☐ |
| Create volunteer handbook | Project Lead | Week 4-5 | ☐ |
| Train lead volunteers on calendar | Project Lead | Week 5 | ☐ |
| Create communication templates | Coordinator | Week 5 | ☐ |
| Pilot scheduling system | Project Lead | Week 5 | ☐ |
| Go live with coordination system | Project Lead | Week 6 | ☐ |

## Area 4: Dispatch Workflow

| Task | Owner | Timeline | Status |
| --- | --- | --- | --- |
| Define 5-stage workflow process | Project Lead | Week 3 | ☐ |
| Create quality classification guide | Project Lead | Week 3 | ☐ |
| Set up intake/assessment station | Coordinator | Week 4 | ☐ |
| Set up sorting station | Coordinator | Week 4 | ☐ |
| Set up dispatch staging area | Coordinator | Week 4 | ☐ |
| Create sorting checklist | Project Lead | Week 4 | ☐ |
| Create packing guidelines | Project Lead | Week 4 | ☐ |
| Schedule sorting sessions (2x/week) | Coordinator | Week 4 | ☐ |
| Create standard pack templates | Project Lead | Week 5 | ☐ |
| Create dispatch receipt template | Coordinator | Week 5 | ☐ |
| Train volunteers on workflow | Project Lead | Week 5 | ☐ |
| Pilot new workflow | Project Lead | Week 5 | ☐ |
| Go live with dispatch system | Project Lead | Week 6 | ☐ |

## Area 5: Operations Reporting

| Task | Owner | Timeline | Status |
| --- | --- | --- | --- |
| Define key metrics to track | Project Lead | Week 3 | ☐ |
| Create daily dashboard template | IT Volunteer | Week 4 | ☐ |
| Create weekly report template | IT Volunteer | Week 4 | ☐ |
| Create monthly report template | IT Volunteer | Week 4 | ☐ |
| Set up automated calculations | IT Volunteer | Week 4 | ☐ |
| Create metric definitions document | Project Lead | Week 4 | ☐ |
| Set up Google Forms for feedback | IT Volunteer | Week 5 | ☐ |
| Train volunteers on data entry | Project Lead | Week 5 | ☐ |
| Create report distribution list | Coordinator | Week 5 | ☐ |
| Schedule report generation times | Project Lead | Week 5 | ☐ |
| Go live with reporting system | Project Lead | Week 6 | ☐ |

# Phase 3: Launch (Weeks 7-8)

| Task | Owner | Timeline | Status |
| --- | --- | --- | --- |
| Conduct full system training | Project Lead | Week 7 | ☐ |
| Perform end-to-end system test | Project Lead | Week 7 | ☐ |
| Address any issues identified | IT Volunteer | Week 7 | ☐ |
| Communicate go-live date | Coordinator | Week 7 | ☐ |
| Launch all systems simultaneously | Project Lead | Week 8 | ☐ |
| Monitor closely during first week | Project Lead | Week 8 | ☐ |
| Collect feedback from all stakeholders | Coordinator | Week 8 | ☐ |
| Make rapid adjustments as needed | Project Lead | Week 8 | ☐ |

# Phase 4: Optimization (Weeks 9-12)

| Task | Owner | Timeline | Status |
| --- | --- | --- | --- |
| Review first month metrics | Project Lead | Week 9 | ☐ |
| Identify bottlenecks and issues | Project Lead | Week 9 | ☐ |
| Gather volunteer feedback | Coordinator | Week 9 | ☐ |
| Gather donor feedback | Coordinator | Week 10 | ☐ |
| Gather collection team feedback | Coordinator | Week 10 | ☐ |
| Refine processes based on feedback | Project Lead | Week 10-11 | ☐ |
| Update documentation | Coordinator | Week 11 | ☐ |
| Conduct refresher training | Project Lead | Week 11 | ☐ |
| Celebrate successes with team | Project Lead | Week 12 | ☐ |
| Document lessons learned | Project Lead | Week 12 | ☐ |
| Plan for continuous improvement | Project Lead | Week 12 | ☐ |

# Notes & Action Items

☐ _________________________________________________________________________________

☐ _________________________________________________________________________________

☐ _________________________________________________________________________________

☐ _________________________________________________________________________________

☐ _________________________________________________________________________________

☐ _________________________________________________________________________________

☐ _________________________________________________________________________________

☐ _________________________________________________________________________________

☐ _________________________________________________________________________________

☐ _________________________________________________________________________________